## DIEGO Tuesday 325
Status Report for Team #5 Crash Report
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-25 |  | Overall Status: | Green
Contact: | Diego La Rosa Giraud |  | Explanation: | We have met all the requirements for yesterday and on track for today
Prepared By: | Diego La Rosa Giraud | scrum master
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Simon Zhu | Created, populated, and connected database to the app
Xin Ran Fang | Implemented the Spring Boot MVC app structure
Xin Ran Fang | Created and tested CRUD methods
Diego La Rosa Giraud | Used JavaMailSender to send customers emails
Sydney Kim | Set up the 3rd party API and got our access key
Team | Designed ERD, Class Diagrams, and flowcharts for the project
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Design and connect database |  |  | Green | 2025-03-24 | Completed/ 100%
Set up Spring Boot MVC app |  |  | Green | 2025-03-24 | Completed/ 100%
Have CRUD methods and test cases |  |  | Green | 2025-03-24 | Completed/ 100%
Set up 3rd party API |  |  | Green | 2025-03-24 | Completed/ 100%
Send emails to users |  |  | Green | 2025-03-25 | Completed/ 100%
Write 3rd party API test cases |  |  | Green | 2025-03-26 | Started coding it/ 35%
Create simple UI web app for CRUD operations |  |  | Green | 2025-03-26 | Started / 40%
Complete slides |  |  | Green | 2025-03-26 | Slides & theme selected / 33%
Integrate 3rd party API with email sending |  |  | Green | 2025-03-27 | Emails completed / 25%
Practice for presentation |  |  | Green | 2025-03-27 | Not started / 0%
Streach Goals
Create map UI showing insidents |  |  | Green | 2025-03-28 | Not started / 0%
Display specific number of crashes per year/month/week by city |  |  | Green | 2025-03-28 | Not started / 0%
Show users their last reports |  |  | Green | 2025-03-28 | Not started / 0%

## SYDNEY Wednesday 326
Status Report for Team #5 Crash Report
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-26 |  | Overall Status: | Green
Contact: | Sydney Kim |  | Explanation: | We've stayed on track for the past 3 days, and have discussed large structural changes to what we worked on yesterday.
Prepared By: | Sydney Kim | scrum master
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Simon Zhu | Writing tests for the 3rd party API
Xin Ran Fang | Finished writing tests for CRUD endpoints
Diego La Rosa Giraud | Implemented front end and related endpoints for DB management etc.
Sydney Kim | Implemented third party API related classes, wrote script/completed slides
Team | Created slides, discussed API decisions, researched different methods for integration
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Design and connect database |  |  | Green | 2025-03-24 | Completed/ 100%
Set up Spring Boot MVC app |  |  | Green | 2025-03-24 | Completed/ 100%
Have CRUD methods and test cases |  |  | Green | 2025-03-24 | Completed/ 100%
Set up 3rd party API |  |  | Green | 2025-03-24 | Completed/ 100%
Send emails to users |  |  | Green | 2025-03-25 | Completed/ 100%
Write 3rd party API test cases |  |  | Green | 2025-03-26 | Continuing / 70%
Create simple UI web app for CRUD operations |  |  | Green | 2025-03-26 | Continuing / 90%
Complete slides |  |  | Green | 2025-03-26 | Just have to pick a project name / 95%
Integrate 3rd party API with email sending |  |  | Green | 2025-03-27 | Waiting on 3rd party API integration / 50%
Practice for presentation |  |  | Green | 2025-03-27 | Script written, not practiced yet / 10%
Fully test 3rd party API |  |  | Green | 2025-03-27 | Discussed and implementing / 30%
Stretch Goals
Create map UI to display incidents |  |  | Green | 2025-03-28 | Not started / 0%
Display specific number of crashes per year/month/week by city |  |  | Green | 2025-03-28 | Not started / 0%
Show users their last reports |  |  | Green | 2025-03-28 | Not started / 0%

## SIMON Thursday 327
Status Report for Team #5 Crash Report
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-27 |  | Overall Status: | Green
Contact: | Simon Zhu |  | Explanation:
Prepared By: | Simon Zhu | scrum master
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Simon Zhu | adjustmnets to sql schema, integrating another 3rd party api endpoint, internal crud api
Xin Ran Fang | tests for internal crud, stubs, and refactoring project
Diego La Rosa Giraud | front end integration, front end ui
Sydney Kim | 3rd party api exploration, internal crud api
Team | presentation decisions, implementation ideas, updates
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Design and connect database |  |  | Green | 2025-03-24 | Completed/ 100%
Set up Spring Boot MVC app |  |  | Green | 2025-03-24 | Completed/ 100%
Have CRUD methods and test cases |  |  | Green | 2025-03-24 | Completed/ 100%
Set up 3rd party API |  |  | Green | 2025-03-24 | Completed/ 100%
Send emails to users |  |  | Green | 2025-03-25 | Completed/ 100%
Write 3rd party API test cases |  |  | Yellow | 2025-03-26 | Continuing / 70%
Create simple UI web app for CRUD operations |  |  | Yellow | 2025-03-26 | Continuing / 90%
Complete slides |  |  | Yellow | 2025-03-26 | Just have to pick a project name / 95%
Integrate 3rd party API with email sending |  |  | Green | 2025-03-27 | Waiting on 3rd party API integration / 80%
Practice for presentation |  |  | Green | 2025-03-27 | Script written, not practiced yet / 25%
Fully test 3rd party API |  |  | Green | 2025-03-27 | Discussed and implementing / 60%
Stretch Goals
Create map UI to display incidents |  |  | Green | 2025-03-28 | Not started / 0%
Display specific number of crashes per year/month/week by city |  |  | Green | 2025-03-28 | Not started / 0%
Show users their last reports |  |  | Green | 2025-03-28 | Not started / 0%

## XIN RAN Friday 328
Status Report for Team #5 Crash Report
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-28 |  | Overall Status: | Green
Contact: | Xin Ran Fang |  | Explanation: | We have met all the requirements for yesterday and on track for today
Prepared By: | Xin Ran Fang | scrum master
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Simon Zhu | Adjust the SQL schema, refactore the project, and add E-mail integration into the application, make sure that the API will be called every 5 min automatically.
Diego La Rosa Giraud | Work on front end, make sure UI is integrated with the database.
Sydney Kim | Work on 3rd party API, figure out how to retrieve coordinate bounds for cities of user's choice, work on presentation slides and script.
Xin Ran Fang | Work on ERD, flowchart and UML.
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Design and connect database |  |  | Green | 2025-03-24 | Completed/ 100%
Set up Spring Boot MVC app |  |  | Green | 2025-03-24 | Completed/ 100%
Have CRUD methods and test cases |  |  | Green | 2025-03-24 | Completed/ 100%
Set up 3rd party API |  |  | Green | 2025-03-24 | Completed/ 100%
Send emails to users |  |  | Green | 2025-03-25 | Completed/ 100%
Write 3rd party API test cases |  |  | Green | 2025-03-26 | Completed/ 100%
Create simple UI web app for CRUD operations |  |  | Green | 2025-03-26 | Completed/ 100%
Complete slides |  |  | Green | 2025-03-26 | Completed/ 100%
Integrate 3rd party API with email sending |  |  | Green | 2025-03-27 | Completed/ 100%
Practice for presentation |  |  | Green | 2025-03-27 | Completed/ 100%