## Status Report
Status Report for Team #5 Crash Report
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-25 |  | Overall Status: | Green
Contact: | Diego La Rosa Giraud |  | Explanation: | We have met all the requirements for yesterday and on track for today
Prepared By: | Diego La Rosa Giraud | scrum master
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Simon Zhu | Created, populated, and connected database to the app
Xin Ran Fang | Implemented the Spring Boot MVC app structure
Xin Ran Fang | Created and tested CRUD methods
Diego La Rosa Giraud | Used JavaMailSender to send customers emails
Sydney Kim | Set up the 3rd party API and got our access key
Team | Designed ERD, Class Diagrams, and flowcharts for the project
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Desing and connect database |  |  | Green | 2025-03-24 | Completed/ 100%
Set up Spring Boot MVC app |  |  | Green | 2025-03-24 | Completed/ 100%
Have CRUD methods and test cases |  |  | Green | 2025-03-24 | Completed/ 100%
Set up 3rd party API |  |  | Green | 2025-03-24 | Completed/ 100%
Send emails to users |  |  | Green | 2025-03-25 | Completed/ 100%
Write 3rd party API test cases |  |  | Green | 2025-03-26 | Started coding it/ 35%
Create simple UI web app for CRUD operations |  |  | Green | 2025-03-26 | Started / 40%
Complete slides |  |  | Green | 2025-03-26 | Slides & theme selected / 33%
Integrate 3rd party API with email sending |  |  | Green | 2025-03-27 | Emails completed / 25%
Practice for presentation |  |  | Green | 2025-03-27 | Not started / 0%
Streach Goals
Create map UI showing insidents |  |  | Green | 2025-03-28 | Not started / 0%
Display specific number of crashes per year/month/week by city |  |  | Green | 2025-03-28 | Not started / 0%
Show users their last reports |  |  | Green | 2025-03-28 | Not started / 0%