## XINRAN Friday 328
Status Report for Team #5 Crash Report
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2025-03-28 |  | Overall Status: | Green
Contact: | Xin Ran Fang |  | Explanation: | We have met all the requirements for yesterday and on track for today
Prepared By: | Xin Ran Fang | scrum master
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Simon Zhu | Adjust the SQL schema, refactore the project, and add E-mail integration into the application, make sure that the API will be called every 5 min automatically.
Diego La Rosa Giraud | Work on front end, make sure UI is integrated with the database.
Sydney Kim | Work on 3rd party API, figure out how to retrieve coordinate bounds for cities of user's choice, work on presentation slides and script.
Xin Ran Fang | Work on ERD, flowchart and UML.
ID # | Key Issues |  | Action Plan |  |  | Status
None
Critical Milestones |  |  | Health | Due Date | Comment/Status %
Design and connect database |  |  | Green | 2025-03-24 | Completed/ 100%
Set up Spring Boot MVC app |  |  | Green | 2025-03-24 | Completed/ 100%
Have CRUD methods and test cases |  |  | Green | 2025-03-24 | Completed/ 100%
Set up 3rd party API |  |  | Green | 2025-03-24 | Completed/ 100%
Send emails to users |  |  | Green | 2025-03-25 | Completed/ 100%
Write 3rd party API test cases |  |  | Green | 2025-03-26 | Completed/ 100%
Create simple UI web app for CRUD operations |  |  | Green | 2025-03-26 | Completed/ 100%
Complete slides |  |  | Green | 2025-03-26 | Completed/ 100%
Integrate 3rd party API with email sending |  |  | Green | 2025-03-27 | Completed/ 100%
Practice for presentation |  |  | Green | 2025-03-27 | Completed/ 100%